VTS Committee – Revised Work Programme 2002-2006

Revised at VTS19, Sept. 2003

| Task | Estimate No. of Sessions | Comments | Working Group |
| --- | --- | --- | --- |
| - Review - VTS Manual - IMO Guidelines on VTS | 5-6 | See note 1 | Ops, Tech, Personnel & Training (P&T) |
| 2 Develop a draft IALA Vision of the Future for VTS | 3-4 |  | Ops |
| 3 Develop a recommendation on the performance requirements for VTS equipment. | 4-5 |  | Ops |
| 4 Develop a recommendation on generic operational procedure for VTS | 2-3 |  | Ops |
| 5 Develop Guidelines for the application of internationally adopted symbology for use in VTS centres and co-ordinate with IEC. | 4-6 |  | Ops, Tech |
| 6 Develop Guidelines for the technical specification of VTS equipment | 4-5 |  | Tech |
| 7 Develop guidelines on data exchange between VTS system. | 4-5 |  | Tech |
| 8 Develop Guidelines on VTS operator workload staffing levels - collect information on staff levels in accordance with service levels - develop guidelines on approaches to VTS Operator Workload Staffing Levels | 5-6 |  | P&T |
| 9 Consider Refresher Training for VTS Personnel | 3-4 |  | P&T |
| 10 Finalize Guidelines on Categorization of VTS / VTS Risk Mitigation | 2-3 |  | Ops |
| 11 Review IALA VTS documentation to ensure Security Issues are addressed where appropriate. | On going | Following IMO ongoing work | Ops, Tech, P&T |

Monitoring Items

| M1 Monitor the use by members of the IALA Guidelines on Risk Management as applied to VTS | Continuous | Rapporteur see note 2 |
| --- | --- | --- |
| M2 Monitor the impacts of AIS on VTS staffing and training | Continuous | Rapporteur see note 3 |

Deferred Items

| D1 Review Recommendation V-103 and update as necessary | Defer | see note 4 |
| --- | --- | --- |
| D2 Review Model Course V-103/1 and update as necessary | Defer | see note 4 |
| D3 Review Model Course V-103/2 and update as necessary | Defer | see note 4 |

Notes:

1.	Before reviewing IMO Resolution A. 857(20), Guidelines on VTS, it should be determined whether there is an urgent and compelling need for the Resolution to be revised.   If this is so, the reasons should be explained fully so that Administrations can prepare and submit proposals to the IMO Maritime Safety Committee for the item to be included on the work programme of the Sub-Committee on Safety of Navigation.  It should also be borne in mind when carrying out the review that this Resolution is “foot-noted” in Regulation 12 of the revised Chapter V of the SOLAS Convention.  The Committee noted that the VTS Manual revision schedule has been realigned by the Secretary General to correspond with VTS Symposiums.  Accordingly, the next edition of the manual will reflect major changes and will be completed for issue in 2008.

- This item has been transferred from the Operations Committee work proposals.  The Council may change this priority if the monitoring programme indicates that IALA needs to take some action on behalf of its Members.  Topics being monitored will not normally appear in the work targets for each session unless the Council approves specific action.

- The Council may change this priority if the monitoring programme indicates that IALA needs to take some action on behalf of its Members.  Topics being monitored will not normally appear in the work targets for each session unless the Council approves specific action.

- Recommendation V-103 and its model courses should not be changed until a number of Competent Authorities and VTS Training Institutes have gained experience with them and are therefore able to comment on the changes that may be necessary.  In addition, the Recommendation and model courses have recently been endorsed by IMO and it could be prejudicial to the interests of IALA for changes to be made to the documents too quickly.  In this regard, changes are not normally made to IMO documents at less than five-year intervals.

Revised Work Plan

|  |  | Session 1 | Session 2 | Session 3 | Session 4 | Session 5 | Session 6 | Session 7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | WG | VTS17 | VTS18 | VTS19 | VTS20 | VTS21 | VTS22 | VTS23 |
| Task 1 | Ops, Tech, PandT | X | X | X | X | X | X | X |
| Task 2 | Ops | X | X | X | X |  |  |  |
| Task 3 | Tech | X | X | X | X | X |  |  |
| Task 4 | Ops |  |  | X | X | X |  |  |
| Task 5 | Ops, Tech | X | X | X | X |  | X | X |
| Task 6 | Tech |  | X | X | X | X | X |  |
| Task 7 | Tech | X | X | X | X | X |  | X |
| Task 8 | PandT | X | X | X | X | X | X |  |
| Task 9 | PandT |  | X | X | X |  |  |  |
| Task 10 | Ops | X |  | X | X | X |  |  |
| Task 11 | Ops, Tech, PandT | X | X | X | X | X | X |  |
| Tasks to be monitored |  |  |  |  |  |  |  |  |
| Task M1 | Monitor – Report by Rapporteur at each Session |  |  |  |  |  |  |  |
| Task M2 | Monitor – Report by Rapporteur at each Session |  |  |  |  |  |  |  |
| Items Deferred |  |  |  |  |  |  |  |  |
| Task D1 | Deferred – Pending the gaining of experience in the use of the Recommendation V-103 and model courses. |  |  |  |  |  |  |  |
| Task D2 |  |  |  |  |  |  |  |  |
| Task D3 |  |  |  |  |  |  |  |  |

* Dec 2003 - note, new Monitoring Item may be added – Monitor the work of PIANC.