# IALA VTS MANUAL

# WORK TARGETS ACHEIVED AT VTS 24 AND WORK PROGRAMME FOR VTS25

The Work Plan (Annex A) is attached and reflects the status of Chapters on completion of VTS24.    Outstanding chapters are due for completion and Committee approval at VTS25.

Following completion of session VTS25 all chapters will be scrutinised for editorial consistency and then posted on the IALA Committee website.   Committee members will be invited to e-mail any points for correction by August 2007, following which the Committee will be invited at VTS26 to adopt the Manual for publication.

Annex A:  IALA VTS Manual - Revised Work Plan – 12 March 2007

# Annex A:  IALA VTS MANUAL - REVISED WORK PLAN – 12 MARCH 2007

| Sect | Chapter No. | Title | Author | Initiate Drafting | Draft for Circulation to VTS Committee | Final version to for agreement | Drafting Status | Approval Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Preface | Editor | VTS 22 | VTS 24 | VTS 25 |  |  |
|  | 1 | Introduction | Editor | VTS 20 | VTS 21 | VTS 21 | Completed | Completed |
|  | 2 | Legal Framework | Editor | VTS 21 | VTS 21 | VTS 22 | Completed | Completed |
|  | 3 | Regulation of VTS | Editor | VTS 21 | VTS21 | VTS 22 | Completed | Completed |
|  | 4 | Objectives of VTS | WG1(+ 2/3) | VTS 20 | VTS 21 | VTS 22 | Completed | Completed |
|  | 5 | Types and Functions of Traffic Services | WG1 (+2/3) | VTS 21 | VTS 22 | VTS 23 | Completed | Completed |
|  | 6 | Principles of Traffic Management | WG1 | VTS 22 | VTS 23 | DS | Completed | Completed |
| 2 | 7 | Determining the need for a VTS | WG1 & 2 | VTS 20 | VTS 22 | VTS 23 | Completed | Completed |
|  | 8 | Planning and Organisation | WG 1 | VTS 20 | VTS 22 | DS | Completed | Completed |
|  | 9 | Procurement Considerations | WG2 | VTS 22 | VTS 23 | DS | Completed | Completed |
|  | 10 | VTS Equipment | WG2 | VTS 20 | VTS 23 | DS | Completed | Completed |
|  | 11 | VTS Personnel | WG3 | VTS 21 | VTS 22 | VTS 23 | Completed | VTS 25 |
|  | 12 | Training and Qualification | WG3 | VTS 22 | VTS 23 | DS | Completed | VTS 25 |
| 3 | 13 | Promulgation of VTS Information | Editor | VTS 22 | VTS 22 | VTS 23 | Completed | Completed |
|  | 14 | Administrative Requirements | WG1 | VTS 24 | VTS 25 |  | Completed | VTS 25 |
|  | 15 | Archives and Records | WG2 | VTS 24 | VTS 25 |  | Completed | VTS 25 |
|  | 16 | Public Information | WG3 | VTS 23 | DS | VTS24 | VTS 25 | VTS 25 |
|  | 17 | VTS Operational Procedures | WG1 | DS | VTS 24 | VTS 24 | Completed | VTS 25 |

VTS 25	 - Mar 2007		VTS 26	- Sep 2007