| From: ANM8 | ANM8-output-09 |
| --- | --- |
| To: All IALA Committees and Secretariat | October 2006 |

Action Plan

- Update of the IALA Dictionary

- Introduction

The ANM committee was asked to co-ordinate the update of the IALA Dictionary. Considering the evolution of the technology and various management tools now available, the IALA is suggesting a revision of this "dictionary" involving the contribution of its committees. The following action plan was prepared.

- Action Plan

|  | Task | Responsibility | Target Date |
| --- | --- | --- | --- |
| 1 | Convert the existing paper version of the sections of the dictionary in PDF format (electronic version) | IALA Secretariat | Nov. 2006 |
| 2 | Post the PDF version on the IALA website and send an invitation to IALA Members to participate to the revision of the Dictionary by sending their input to the Secretariat by Sept. 2007 | IALA Secretariat | Nov. 2006 |
| 3 | Convert the existing paper version of the sections of the dictionary in MS Word format (electronic version) | IALA Secretariat | Sept.2007 |
| 4 | Send the MS Word documents and input from IALA members to IALA Committees | IALA Secretariat | Sept.2007 |
| 5 | Review and provide revision input to the dictionary | IALA Committees | Oct.2008 |
| 6 | Consolidation of inputs | IALA Secretariat | March 2009 |
| 7 | Preparation of final version | ANM Committee and IALA Secretariat | Oct. 2009 |
| 8 | Publications (Paper and Internet Version) | IALA Secretariat | April 2010 |

The following table details the responsibilities of each IALA Committees in relation to the chapters of the dictionary.

| Chapter | Subject | Committee |
| --- | --- | --- |
| 1 | General Terms | ANM |
| 2 | Visual Aids | EEP |
| 3 | Audible Aids | EEP |
| 4 | Radio Aids | e-NAv |
| 5 | Automatic and Remote Control. Reliability | EEP / e-Nav |
| 6 | Power Supplies for Stations | EEP (IALABATT) |
| 7 | Civil Engineering works | EEP / ANM |
| 8 | Floating Equipment | EEP |

ANM8-WG2-output-dictionary_action_plan.doc